## Sheet1
[11 empty] | oct08-oct30 | Nov01-Nov07 | Nov08-Nov15 | Nov 1-15
|  | Aug 14-24 | Aug 24-30 | Aug 30-31 | Sept 01-15 | Sept 16-30 | oct 01-08 | Oct 08-Oct 28 | Oct 29 -Nov1 | Nov2-Nov4
Finalizing Project Idea | Project Topic
Feasibility Analysis | Feasibility Report
Plan the work to be done in different phases of software
development | Project Plan
Requirements collections through online surveys and | Questions are framed and survey responses
discussions | are collected and the requirements are
gathered.
Analysis of Requirements | Risk Management Plan,Survey Response
Analysis, SRS, Test Plan, Quality Assurance
Plan, Configuration Management Plan
Design Phase | Design Document and all Low level designs
Coding and Unit Testing of modules | Coding and Unit testing of modules as per the
SRS document
Testing the System | System is tested as per the system test plan
prepared before and test report
Finalizing the documents and Deployment | Final Product, User Manual, Installation Manual,
and Deployment Plan